| ### Harvard ManageMentor —LEADING AND MOTIVATING TOOLS |  |  |  |
| --- | --- | --- | --- |
| Group Learning Project Plan: Develop a Vision Statement with Your Team |  |  |  |
| Use this learning project plan to define your project, schedule project activities, identify necessary resources, track your progress, and reflect on your project outcomes. Consider adding more or different reflection questions in Part III to fit your project. |  |  |  |
| Part I. Define your group learning project |  |  |  |
| Project description: |  |  |  |
| The project involves clarifying an effective vision for your unit or department and expressing the vision in a short statement or paragraph. Project team members will research vision statements created by other companies or departments and, together, complete the Worksheet for Developing a Vision (found in the Tools section of the Leading and Motivating topic). The final outcome of the project will be a refined vision statement that meets all criteria for effectiveness listed in the worksheet. |  |  |  |
| Project goal(s): |  |  |  |
| Help team members practice defining and expressing a vision that will inspire everyone in the team to work together in order to achieve the desired future state expressed in the vision. |  |  |  |
| Project participants: |  |  |  |
| Part II. Plan and track your progress |  |  |  |
| Project step | Resources needed | Target completion date | Check when completed |
| - Gather information for the team’s vision. Meet with other team members to decide what information is needed to define a vision for the team. Information may include the organization’s or department’s mission, vision, or strategy; customers’ needs and priorities; and trends in the marketplace or competition. Decide who will gather what information, then have team members obtain the information they’re responsible for collecting. | - Steps for Formulating a Vision (found in the Steps section of the Harvard ManageMentor topic Leading and Motivating) - Part I of the Worksheet for Developing a Vision (found in the Tools section of the Leading and Motivating topic) | Day 7 |  |
| - Craft the team’s vision statement. Meet with team members to analyze all the information gathered in Step 1. Together, discuss what the analysis suggests about a possible vision for your team. During the meeting, craft a set of sentences or a short paragraph that expresses what you all see as the team’s vision. | - Part II of the Worksheet for Developing a Vision (found in the Tools section of the Leading and Motivating topic) | Day 21 |  |
| - Evaluate the vision statement’s effectiveness. During the same meeting as step 2, or in a subsequent meeting, determine through consensus how well the vision statement your team has crafted meets the criteria for an effective vision. | - Characteristics of an effective vision (found in the “Crafting a Vision That Others Will Follow” section of the Leading and Motivating topic) - Part III of the Worksheet for Developing a Vision (found in the Tools section of the Leading and Motivating topic) | Day 21 |  |
| - Refine the vision statement as needed. Meet with team members to revise or rewrite the vision statement as necessary to ensure that it meets all the criteria of effectiveness. | - Part III of the Worksheet for Developing a Vision (found in the Tools section of the Leading and Motivating topic) - Poster board or other materials for displaying the vision statement if desired | Day 28 |  |
| - Participate in a project debrief session to: - Discuss as a group the questions listed in Part III of this tool (below). - Decide what other groups in the organization would benefit from seeing the vision statement produced by the team. | - Discussion questions found in Part III of this tool | Day 30 |  |
| Part III. Reflect on your project outcomes |  |  |  |
| At the conclusion of your group learning project, use the following questions to reflect on your project experience and outcomes. |  |  |  |
| What did you learn as a result of the project? |  |  |  |
| What were your biggest surprises during, or at the conclusion of, your project? |  |  |  |

What were the biggest challenges during the project?

Describe any tangible impacts that your vision statement had, or may have, on the organization.

Based on your insights gained from the project experience, what will you or your group do differently going forward?

What suggestions or tips would you give others regarding how to define and communicate a compelling vision?

Part IV. Share your results

Share your findings with others outside of your group: At the conclusion of the project, consider sharing your lessons learned and project results with others in your organization. For example, you could hold an information-sharing session over lunch or post suggestions on a discussion forum.